## 90-Day Sprint
90-DAY SOVEREIGNTY SPRINT PLANNER
Week | Phase | Key Activities | Deliverable | Owner | Status | Dependencies | Notes
1 | Discovery | Build cloud/AI services inventory | Services Register v1 | Cloud Arch Lead | Not Started | Finance data
1 | Discovery | Assign preliminary owners | Owner matrix draft | CTO | Not Started | HR org chart
2 | Discovery | Map identity dependencies | Identity Dependency Map | Identity Lead | Not Started | Services Register
2 | Discovery | Document decision authority gaps | Gap analysis report | Governance Lead | Not Started | Interviews
3 | Foundation | Create ADRs for top 10 past decisions | 10 completed ADRs | Architecture Lead | Not Started | Historical docs
3 | Foundation | Establish AI model registry | Model Registry v1 | AI Platform Lead | Not Started | AI inventory
4 | Foundation | Run first identity failover simulation | Simulation report | DR Manager | Not Started | Test environment
4 | Foundation | Finalize decision rights map | Decision Rights Map v1 | CTO | Not Started | Exec approval
5 | Remediation | Close Gap #1: [TBD from assessment] | Evidence package | TBD | Not Started | Budget approval
6 | Remediation | Close Gap #2: [TBD from assessment] | Evidence package | TBD | Not Started
7 | Remediation | Close Gap #3: [TBD from assessment] | Evidence package | TBD | Not Started
8 | Remediation | Close Gap #4: [TBD from assessment] | Evidence package | TBD | Not Started
9 | Validation | Run multi-service DR simulation | DR test report | DR Manager | Not Started | All remediation
10 | Validation | Complete AI autonomy ceiling review | L0-L5 assignments | AI Council | Not Started | Model registry
11 | Validation | Executive governance review | Governance assessment | CIO | Not Started | All deliverables
12 | Close | Board sovereignty briefing | Board presentation | CIO | Not Started | Exec approval
12 | Close | Establish ongoing operating rhythm | Operating calendar | CTO | Not Started | All workstreams