## Failover Test Log
FAILOVER TEST LOG
Document all failover tests with results, duration, and lessons learned
SUMMARY
| Total Tests: |  | Pass Rate: |  | Avg Duration:
Test ID | Test Date | System/Service | Failover Type | Primary → Secondary | Test Scenario | Result | RTO Target (min) | Actual Duration (min) | Data Loss (RPO) | Issues Encountered | Lessons Learned
FT-2024-001 | 2024-01-15 | Identity Provider | Full Failover | Azure AD → Okta | Complete IdP outage simulation | Pass | 30 | 22 | None | Minor DNS propagation delay | Pre-stage DNS changes for faster cutover
FT-2024-002 | 2024-02-20 | Database Cluster | Read Replica Promotion | Primary → DR Region | Primary database failure | Pass | 15 | 18 | < 1 min | 3 transactions in flight lost | Implement connection draining before failover
FT-2024-003 | 2024-03-10 | Web Application | Load Balancer Failover | US-East → US-West | Regional outage | Partial | 10 | 45 | None | Session state not replicated | Implement distributed session store
FT-2024-004 | 2024-04-05 | Email System | Provider Failover | M365 → Google Workspace | Full provider outage | Fail | 60 | 180 | 2 hours | MX record TTL too high, calendar sync failed | Reduce TTL to 5 min, test calendar separately
FT-2024-005 | 2024-05-12 | Payment Processing | Gateway Failover | Stripe → Backup Gateway | Primary gateway down | Pass | 5 | 3 | None | None | Automated failover working as designed

## Test Schedule
FAILOVER TEST SCHEDULE
Plan and track scheduled failover tests by system criticality
System/Service | Criticality | Test Frequency | Last Test Date | Next Test Due | Owner
Identity Provider (Primary) | Critical | Quarterly | 2024-04-15 | 2024-07-15 | [Name]
Primary Database | Critical | Quarterly | 2024-03-20 | 2024-06-20 | [Name]
Core Application Tier | Critical | Quarterly | 2024-05-01 | 2024-08-01 | [Name]
Email/Collaboration | High | Semi-Annual | 2024-01-10 | 2024-07-10 | [Name]
Payment Processing | Critical | Monthly | 2024-05-12 | 2024-06-12 | [Name]
Data Warehouse | High | Semi-Annual | 2024-02-28 | 2024-08-28 | [Name]
CRM System | High | Semi-Annual | 2024-04-05 | 2024-10-05 | [Name]
Backup/Recovery | Critical | Quarterly | 2024-03-15 | 2024-06-15 | [Name]

## Test Template
PRE-TEST PREPARATION
Test ID: | [Auto-generate: FT-YYYY-###]
System/Service: | [Enter system name]
Test Date/Time: | [Scheduled date and time]
Test Lead: | [Name]
Participants: | [List all participants]
Stakeholders Notified: | ☐ Yes ☐ No
Rollback Plan Documented: | ☐ Yes ☐ No
TEST PARAMETERS
Failover Type: | [Full/Partial/DNS/etc.]
Primary System: | [Current production]
Secondary System: | [Failover target]
RTO Target: | [X] minutes
RPO Target: | [X] minutes / Zero
Test Scenario: | [Describe what failure is being simulated]
Success Criteria: | [Define what constitutes pass/fail]
TEST EXECUTION
Failover Initiated: | [Timestamp]
Failover Complete: | [Timestamp]
Actual Duration: | [X] minutes
Data Loss Observed: | [None / Amount]
User Impact: | [Describe any user-facing issues]
ROLLBACK (if performed)
Rollback Initiated: | [Timestamp or N/A]
Rollback Complete: | [Timestamp or N/A]
Rollback Duration: | [X] minutes or N/A
POST-TEST ANALYSIS
Test Result: | ☐ Pass ☐ Partial ☐ Fail
Issues Encountered: | [List all issues]
Root Cause (if failed): | [Analysis]
Lessons Learned: | [Key takeaways]
Action Items: | [Required follow-ups with owners and dates]
SIGN-OFF
Test Lead Signature: | _________________ Date: _________
System Owner Signature: | _________________ Date: _________

## Instructions
FAILOVER TEST LOG — INSTRUCTIONS
PURPOSE
Document all failover tests to build institutional knowledge, track improvement over time, and demonstrate due diligence to auditors and leadership.
RECOMMENDED TEST FREQUENCY
• Critical systems: Quarterly (minimum)
• High-criticality systems: Semi-annually
• Medium-criticality systems: Annually
• After any major infrastructure change: Within 30 days
TEST RESULT DEFINITIONS
PASS — Failover completed within RTO, RPO met, no significant issues
PARTIAL — Failover completed but with issues (exceeded RTO, minor data loss, manual intervention required)
FAIL — Failover did not complete, exceeded RPO, or caused unacceptable disruption
LESSONS LEARNED
The most valuable part of testing is learning. Every test should generate at least one lesson, even successful ones. Common lessons include:
• Runbook updates needed
• Configuration drift discovered
• Dependencies not previously documented
• Communication gaps during test
• Automation opportunities identified
GOVERNANCE
• Review test log in quarterly sovereignty reviews
• Report pass rate trend to leadership
• Track time to resolve failed test issues
• Use failures as input to risk register
From "When Clouds Fail" by Steve Oppenheim