## Read Me
CRYPTOGRAPHIC CENSUS AND QUANTUM MIGRATION WORKBOOK
Companion instrument 02 of the When Agents Rule toolkit. Inventory every cryptographic dependency, score its quantum exposure, and assign it to a migration wave you can defend to a regulator.
WHAT THIS WORKBOOK DOES
You cannot migrate cryptography you have not found. This workbook is the finding instrument and the prioritisation instrument in one file.
The census tab records every place cryptography is used. The reference tab tells you which algorithms fall to a quantum computer and what replaces them. The exposure calculator applies the shelf life test: if the years your data must stay confidential plus the years your migration will take exceed the years until a cryptographically relevant quantum computer arrives, that data is already exposed today.
The output is a wave assignment per asset. Wave 1 is what you fund this budget cycle. Everything else has a defensible reason for waiting.
WHERE TO START
Step 1 | Open Planning Assumptions and set your quantum planning horizon. The default is a 2032 planning date. Every priority score in this workbook moves when you change that one cell, which is the point.
Step 2 | Fill the Cryptographic Census tab. Start with anything public facing and anything that protects data with a confidentiality requirement past 2035. Those two categories produce most of your Wave 1.
Step 3 | Complete the Data Shelf Life Test for your major data classes. This is the exhibit that makes the harvest now, decrypt later argument concrete for a CFO.
Step 4 | Read the Migration Dashboard. It gives you wave counts, the assets with no vendor commitment, and the assets that cannot be migrated without hardware replacement.
Step 5 | Send the Vendor PQC Assessment Questionnaire (instrument 05) to every vendor showing No response or Unknown in column N.
HOW TO USE THIS WORKBOOK
Pale yellow cells with blue text | You fill these in. Every other cell is a formula or reference.
Grey cells | Calculated. Do not overwrite; they will recalculate as you enter data.
Row 'EXAMPLE' | A sample row showing the expected format. Delete it before you publish.
Dropdown cells | Click the cell and choose from the list so the scoring formulas resolve.
HOW THIS RELATES TO THE BOOK
The threat model, the economics of delay, and the five year migration structure are set out in When Agents Rule, Chapters 2, 6, 11 and 13. This workbook is the blank register those chapters describe. Regulatory dates and algorithm status in the reference tab were current at the September 2026 build date and should be reverified against NIST, NSA and your own regulators before you brief an executive committee.
Companion toolkit for WHEN AGENTS RULE by Steven Oppenheim. Free for internal use inside your own organization. Not legal, technical, or financial advice. Verify all regulatory dates against primary sources before relying on them.

## Planning Assumptions
PLANNING ASSUMPTIONS
Four numbers drive every score in this workbook. Change them here, not in the formulas.
Assumption | Value | Unit | Basis and source
Current planning year | 2026 | year | Set to the year you are doing this exercise. Drives all shelf life maths.
Quantum planning date (CRQC) | 2032 | year | Your planning assumption for when a cryptographically relevant quantum computer exists. Published estimates cluster between 2030 and 2035 and carry wide uncertainty. Choosing a date is a governance decision, not a physics prediction. Document who approved it.
Assumed enterprise migration duration | 6 | years | How long your full cryptographic migration will realistically take end to end. Published guidance commonly assumes a ten year horizon for large estates; six is a defensible planning figure for a focused programme with executive backing.
Harvest assumption start year | 2020 | year | The year from which you assume adversaries may already have captured traffic. Anything encrypted since this date and still sensitive is in scope for the shelf life test.
DERIVED PLANNING NUMBERS
Derived value | Value | Unit | Why it matters
Years until quantum planning date | 6 | years | The z term in the shelf life test.
Latest defensible migration start year | 2026 | year | If this year is in the past, your migration is already behind its own plan.
Years of traffic potentially already captured | 6 | years | The volume of historic traffic that a future decryption capability could read. This number only grows.
Migration slack remaining | 0 | years | Negative means you cannot finish before your own planning date. That is the number to put in front of a board.
Companion toolkit for WHEN AGENTS RULE by Steven Oppenheim. Free for internal use inside your own organization. Not legal, technical, or financial advice. Verify all regulatory dates against primary sources before relying on them.

## Algorithm Reference
ALGORITHM STATUS AND REPLACEMENT REFERENCE
Status as at the September 2026 build date. Reverify against NIST and NSA publications before using this in a regulatory filing or board paper.
Algorithm in use | Family | Quantum status | Standards aligned replacement | Vulnerability points
RSA 1024 | Public key | Broken by Shor. Already below classical strength floors. | ML-KEM or ML-DSA per purpose | 6
RSA 2048 | Public key | Broken by Shor. Standard enterprise default today. | ML-KEM 768 (KEM) or ML-DSA 65 (signature) | 6
RSA 3072 or 4096 | Public key | Broken by Shor. Larger keys do not help against Shor. | ML-KEM 1024 or ML-DSA 87 | 6
ECDSA P 256 | Public key | Broken by Shor. | ML-DSA 65, or SLH-DSA where signature longevity matters | 6
ECDSA P 384 or P 521 | Public key | Broken by Shor. | ML-DSA 87 or SLH-DSA | 6
ECDH or ECDHE P 256 | Key exchange | Broken by Shor. The key exchange path is the harvest now target. | Hybrid X25519 with ML-KEM 768, then ML-KEM only | 6
X25519 | Key exchange | Broken by Shor. | Hybrid X25519 with ML-KEM 768 | 6
DSA or Diffie Hellman (finite field) | Public key | Broken by Shor. Also legacy by classical standards. | ML-DSA or ML-KEM per purpose | 6
Ed25519 | Public key | Broken by Shor. | ML-DSA 65 or SLH-DSA | 6
3DES | Symmetric | Deprecated on classical grounds regardless of quantum. | AES 256 GCM | 5
RC4 | Symmetric | Broken classically. Should already be gone. | AES 256 GCM | 5
AES 128 | Symmetric | Weakened by Grover. Effective strength reduced, not broken. | AES 256 for data with long confidentiality needs | 3
AES 192 | Symmetric | Weakened by Grover. Acceptable for most horizons. | AES 256 where shelf life exceeds fifteen years | 2
AES 256 | Symmetric | Considered quantum resistant for confidentiality. | No change needed. Confirm mode and key management. | 0
SHA 1 | Hash | Broken classically. Should already be gone. | SHA 384 or SHA 3 384 | 5
SHA 256 | Hash | Reduced margin under Grover but widely accepted. | SHA 384 where long term integrity is required | 2
SHA 384 or SHA 512 | Hash | Considered adequate against known quantum attacks. | No change needed. | 0
ML-KEM (FIPS 203) | PQC key exchange | Quantum resistant. NIST standard. | No change needed. Track parameter guidance. | 0
ML-DSA (FIPS 204) | PQC signature | Quantum resistant. NIST standard. | No change needed. | 0
SLH-DSA (FIPS 205) | PQC signature | Quantum resistant. NIST standard. Larger signatures. | No change needed. Suited to firmware and long lived signing. | 0
Hybrid classical with ML-KEM | Hybrid | Quantum resistant for key exchange while retaining interoperability. | Target state for transport during transition. | 0
Proprietary or vendor undisclosed | Unknown | Cannot be assessed. Treat as worst case until the vendor discloses. | Require disclosure in the next contract cycle. | 6
Unknown | Unknown | Not yet identified. Treat as worst case. | Identify before assigning a migration wave. | 6
Larger RSA and elliptic curve keys do not defend against Shor's algorithm. They raise the size of the quantum computer required, not the difficulty class of the problem. This is the single most common misunderstanding in cryptographic inventories, and it produces plans that migrate key length instead of migrating algorithm family.
SCORING TABLES USED BY THE CENSUS
Dimension | Answer | Points
Shelf life | 0 to 2 years | 0
| 3 to 5 years | 1
| 6 to 10 years | 3
| 11 to 20 years | 5
| Over 20 years or permanent | 6
| Unknown | 6
Migration effort | Low, configuration only | 0
| Medium, code or certificate change | 1
| High, architecture change | 3
| Very high, vendor or hardware dependent | 4
| Unknown | 4
Crypto agility | Configurable without code change | 0
| Code change required | 1
| Firmware update required | 3
| Hardware replacement required | 4
| Unknown | 4
Vendor PQC position | Committed date published | 0
| Roadmap with no date | 2
| No response received | 4
| Not applicable, internally built | 0
| Unknown | 4
Regulatory driver | CNSA 2.0 national security systems | 4
| US federal executive order | 4
| DORA financial sector | 2
| NIS2 critical infrastructure | 2
| Other sector regulation | 2
| Contractual customer requirement | 2
| None identified | 0
MIGRATION WAVE THRESHOLDS
Minimum score | Wave | What the wave means
0 | Wave 4: by 2033 | Low exposure. Migrate on the natural refresh cycle. Track, do not fund separately.
8 | Wave 3: 2029 to 2031 | Migrate during planned platform work. Budget in the outer years.
14 | Wave 2: 2027 to 2029 | Scheduled programme work. Needs a named owner and a funded plan now.
20 | Wave 1: 2026 to 2027 | Fund this budget cycle. Either the data outlives the encryption or a regulator has already set the date.
Companion toolkit for WHEN AGENTS RULE by Steven Oppenheim. Free for internal use inside your own organization. Not legal, technical, or financial advice. Verify all regulatory dates against primary sources before relying on them.

## Cryptographic Census
CRYPTOGRAPHIC CENSUS REGISTER
One row per cryptographic dependency. Columns A to M you fill in. Columns N to T calculate. Aim for breadth before depth: an incomplete census that covers the whole estate beats a perfect census of one platform.
Asset ID | System or asset name | Business owner (named person) | Technical owner | Asset type | Vendor or product | Algorithm in use | Cryptographic purpose | Confidentiality required until (year) | Migration effort | Crypto agility | Vendor PQC position | Regulatory driver | Quantum status | Standards aligned replacement | Shelf life (years) | Shelf life band | Harvest now decrypt later exposure | Migration priority score | Migration wave | Notes and action
CR-001 | Customer portal public TLS termination | L. Fontaine, Digital Channels | R. Nakamura, Network Engineering | Public TLS endpoint | Load balancer appliance, vendor firmware | ECDH or ECDHE P 256 | Key exchange | 2045 | Very high, vendor or hardware dependent | Firmware update required | Roadmap with no date | DORA financial sector | Broken by Shor. The key exchange path is the harvest now target. | Hybrid X25519 with ML-KEM 768, then ML-KEM only | 19 | 11 to 20 years | EXPOSED | 22 | Wave 1: 2026 to 2027 | EXAMPLE ROW. Delete before publishing. Appliance reaches end of support in 2028; PQC support depends on a firmware release the vendor has not dated.
Companion toolkit for WHEN AGENTS RULE by Steven Oppenheim. Free for internal use inside your own organization. Not legal, technical, or financial advice. Verify all regulatory dates against primary sources before relying on them.
Note on G4: Pick from the dropdown so the status, replacement and scoring formulas resolve. If the algorithm is not listed, enter Unknown and record the detail in the Notes column. Unknown scores as worst case on purpose.
Note on I4: The last year this data must remain confidential. Use the regulatory retention period, the contractual obligation, or the lifetime of the person the data describes, whichever is longest. Medical, actuarial, legal and identity data routinely exceed forty years.
Note on R4: Applies the shelf life test. EXPOSED means the years this data must stay confidential plus your assumed migration duration already exceed the years until your quantum planning date, and the algorithm protecting it falls to a quantum attack. Data in this state is exposed today, not in the future.

## Data Shelf Life Test
DATA SHELF LIFE TEST
The board exhibit. For each major data class, does the confidentiality requirement plus the migration duration exceed the time remaining until your quantum planning date?
Data class | Confidentiality required (years) | Class specific migration duration (years) | Encrypted since | Confidentiality expires | Protection margin (years) | Verdict | Consequence if the assumption is wrong
Customer identity and KYC records | 40 | 6 | 2016 | 2066 | -40 | EXPOSED TODAY
Payment and card data | 10 | 4 | 2018 | 2036 | -8 | EXPOSED TODAY
Employee HR and medical records | 45 | 5 | 2015 | 2071 | -44 | EXPOSED TODAY
Intellectual property and source code | 25 | 3 | 2014 | 2051 | -22 | EXPOSED TODAY
Board and M&A material | 20 | 2 | 2017 | 2046 | -16 | EXPOSED TODAY
Contracts and legal privilege | 30 | 3 | 2015 | 2056 | -27 | EXPOSED TODAY
Regulatory filings and audit evidence | 15 | 4 | 2019 | 2041 | -13 | EXPOSED TODAY
Operational telemetry | 3 | 2 | 2022 | 2029 | 1 | MARGINAL
Data classes exposed today | 7 | Confidentiality outlasts the protection. Encrypted traffic captured now becomes readable while it still matters.
Data classes marginal | 1 | Two years or less of slack. A single slipped programme year moves these into exposed.
Worst margin in the estate (years) | -44 | The single number to put on a board slide. Negative means the gap already exists.
Weighted average margin (years) | -21.125 | Useful only as a trend across quarters as the programme advances.
How to read the margin. It is the years remaining until your quantum planning date, minus the years the data must stay confidential, minus the years this class will take to migrate. Positive means you can finish in time. Negative means the exposure already exists and no amount of future effort closes it retroactively, because traffic captured today cannot be un-captured.
With the shipped default assumptions most classes come out negative. That is the finding, not a flaw in the model. Replace the default years with your own retention obligations and your own programme estimates, then change the quantum planning date on the Planning Assumptions tab and watch which classes move. The classes that stay negative across every reasonable assumption are the ones that justify Wave 1 funding.
Companion toolkit for WHEN AGENTS RULE by Steven Oppenheim. Free for internal use inside your own organization. Not legal, technical, or financial advice. Verify all regulatory dates against primary sources before relying on them.

## Migration Dashboard
MIGRATION DASHBOARD
Calculated from the Cryptographic Census tab. No inputs on this sheet.
CENSUS COVERAGE AND EXPOSURE
Measure | Value |  |  | What it tells you
Cryptographic assets recorded | 1 |  |  | Your census breadth. Compare against your CMDB asset count to estimate coverage.
Assets with unknown algorithm | 0 |  |  | Every one of these is a blind spot. Resolve before you claim a complete census.
Assets flagged EXPOSED | 1 |  |  | The harvest now decrypt later population. This is your headline number for a board.
Assets needing hardware replacement | 0 |  |  | These have the longest lead time and the largest capital requirement. Start procurement first.
Assets with no vendor PQC commitment | 1 |  |  | Your migration timeline is capped by these vendors. Escalate commercially, not technically.
Assets under a regulatory deadline | 1 |  |  | The subset where the date is set by someone other than you.
Assets with no named business owner | 0 |  |  | Unowned cryptography does not get migrated. It gets discovered during an incident.
Highest priority score in the estate | 22 |  |  | Twenty eight is the ceiling. Twenty and above is Wave 1.
WAVE ASSIGNMENT
Migration wave | Assets | Share | Of which EXPOSED | Budget implication
Wave 1: 2026 to 2027 | 1 | 100% | 1 | Current budget cycle. Named owner and funded plan required now.
Wave 2: 2027 to 2029 | 0 | 0% | 0 | Next two planning cycles. Include in the multi year capital plan.
Wave 3: 2029 to 2031 | 0 | 0% | 0 | Outer years. Align to platform refresh.
Wave 4: by 2033 | 0 | 0% | 0 | Natural refresh cycle. Track only.
ASSET TYPE CONCENTRATION
Asset type | Count | EXPOSED
Public TLS endpoint | 1 | 1
Internal TLS service | 0 | 0
VPN or tunnel | 0 | 0
Code or artefact signing | 0 | 0
Firmware signing | 0 | 0
Public key infrastructure or CA | 0 | 0
Hardware security module | 0 | 0
Database encryption at rest | 0 | 0
Backup and archive | 0 | 0
Operational technology or embedded device | 0 | 0
Third party API integration | 0 | 0
Companion toolkit for WHEN AGENTS RULE by Steven Oppenheim. Free for internal use inside your own organization. Not legal, technical, or financial advice. Verify all regulatory dates against primary sources before relying on them.