## Read Me
Twelve Month Agent Governance Sprint Tracker
Read this sheet before entering data. It states what the instrument does, what it does not do, and which cells you are expected to change.
WHAT THIS INSTRUMENT IS
A twelve month implementation tracker for an agent governance programme, organised in four quarterly gates rather than as a task list. The unit of tracking is the gate, because a programme that reports eighty percent task completion and fails its gate has learned nothing from the eighty percent.
THE ONE DESIGN DECISION
Every quarter carries an EXIT TEST that a person outside the programme has to be able to verify. Chapter 12 argues that organisational resistance, not technical difficulty, is what stops this work, and the most common form that resistance takes is a programme that stays permanently at ninety percent. An externally verifiable exit test is the defence against that.
The tracker also records CHANGE LOAD on the receiving teams, because the A.R.T. research finding is that change saturation is the most under diagnosed cause of stalled value. A sprint that the receiving team cannot absorb is not progress, it is queue.
HOW TO USE IT
Fill the owner and the target date for each item. Status and percent complete are yours. Everything in grey is calculated: days remaining, whether the gate is at risk, and the single escalation sentence for each row. Update weekly and take the QUARTER GATES sheet to the governance council rather than the item list.
WHAT THIS IS NOT
Not a project management tool and not a substitute for one. The ninety day sequence in the Toolkit Index tells you what to do; this tells you whether it is happening and when to escalate. Not legal, technical or financial advice.
METHOD
From When Agents Rule, Chapters 12, 15 and 16.

## Sprint Items
SPRINT ITEMS
Four quarters, five workstreams. Every item has one owner and one receiving team, because an item with two owners has none. Change load is your judgement of what the receiving team is already absorbing.
IF THE RECEIVING TEAM IS AT HIGH CHANGE LOAD, THE HONEST MOVE IS TO RESEQUENCE RATHER THAN TO PUSH. THE ESCALATION COLUMN WILL SAY SO.
Ref | Quarter | Workstream | Item | Owner (name and role) | Receiving team | Change load on receiver | Target date | Status | Percent complete | Days remaining | Blocked by | Escalation
S01 | Q1 | Discovery | Run the shadow AI discovery sweep across the seven places agents hide
S02 | Q1 | Discovery | Populate the agent inventory with autonomy level and identity tier per system
S03 | Q1 | Discovery | Identify every agent holding a shared service account
S04 | Q1 | Governance | Stand up the governance council with named membership and a quorum rule
S05 | Q1 | Governance | Adopt the governance charter, including the discovery obligation
S06 | Q1 | Finance | Baseline cost per compliant decision for one high volume workload
S07 | Q2 | Controls | Give every L3 and above agent its own workload identity
S08 | Q2 | Controls | Narrow credential scope to the minimum each workload needs
S09 | Q2 | Controls | Build and time the containment path for the highest autonomy system
S10 | Q2 | Reliability | Define the five agent service level indicators per production agent
S11 | Q2 | Regulatory | Classify every system against Annex III and document the Article 6(3) position
S12 | Q2 | Finance | Take the governance business case to the investment committee
S13 | Q3 | Controls | Drill containment with someone other than the author, and record elapsed time
S14 | Q3 | Reliability | Set error budgets stratified by autonomy level and wire them to the deployment gate
S15 | Q3 | Reliability | Sign a reliability contract for each L3 and above deployment
S16 | Q3 | Regulatory | Assemble the regulatory evidence pack for the highest risk system
S17 | Q3 | Governance | Run the first full agent incident rehearsal including communications and reversal
S18 | Q3 | Discovery | Re run the discovery sweep and measure what the first sweep missed
S19 | Q4 | Governance | Report to the board on the quarterly template, with the trend not just the level
S20 | Q4 | Reliability | Review every error budget against actual burn and re set where it was wrong
S21 | Q4 | Regulatory | Close the Article 6(3) documentation and registration position with counsel
S22 | Q4 | Controls | Complete a clean owner handover to prove continuity is real
S23 | Q4 | Finance | Re baseline cost per compliant decision and report the delta against Q1
S24 | Q4 | Discovery | Automate inventory maintenance, because a quarterly sweep is stale within a quarter
Formulas:
Days remaining = IF([Target date]="","",[Target date]-TODAY())

## Quarter Gates
QUARTER GATES
Take this sheet to the council, not the item list. A gate is passed when the named verifier says so, not when the percentage looks acceptable.
Quarter | Exit test (verifiable by someone outside the programme) | Who verifies it | Items in quarter | Complete | Percent | Gate verdict
Q1 | Name every agent in the enterprise, and state for each one its autonomy level and whose credentials it uses | Internal audit or risk
Q2 | Show an agent being stopped, timed, by someone who did not build it | CISO or delegate
Q3 | Produce the evidence pack for one high risk system, on request, within one working day | General counsel or compliance
Q4 | Show the board the same five measures you showed them last quarter, with the direction of travel | Board or risk committee
The exit tests are deliberately harder than the item list. That is the point: a programme can complete every item and still fail to produce the capability, which is why the verifier is someone outside the programme. If a verifier has not been named in column C, the gate cannot be passed at all.